1. UPGRADATION CONTRACT TNRSP 01

| 1 | Contract Package | TNRSP-01 |
| --- | --- | --- |
| 2 | Name of work | Upgrading of roads from Arcot to Ulundurpettai (Elavanasur), Polur - Chengam, Vriddhachalam - Thiruvarur, Jayakondam – Ariyalur, and new bypass roads at Chidambaram, Sirkazhi, Arani, Polur, Thiruvannamalai, Thirukkovilur, Vriddhachalam, Ariyalur and Thiruvarur |
| 3 | Name of Contractor | M/s. KMC - OSC – BSCPL JV. |
| 4 | Name of Consultant | LEA International Ltd. & LEA Associates South Asia Pvt Ltd. (JV) |
| 5 | Original Contract value | 611.7 Crores |
|  | Variation Amount | 62.0 Crores |
| 6 | Contract Estimate as on Today Including Variation | 511.62 Crores |
| 7 | Total length of Project Road | 377.74 km |
| 8 | Physical progress |  |
|  | Achieved | 93.59% |
|  | Target | 100% |
| 9 | Financial progress |  |
|  | Achieved | 95.63% |
|  | Target | 100% |

Status

Road Works : (AS PER NEW RECONFIGURATION)

- Section 4 – 6 no. of ROB’s, Thiruvarur Bypass 0.5 km, Jayakondam – Ariyalur 7.3 Km, Kumbakonam-Thiurvarur 3Km, and Thirukkovilur – Elavanasur Kottai 2.8 Km  total length of 13.6 km has been deleted from Contract as per the instructions from TNRSP.

- As per the recent decision by TNRSP for substantial completion of about 279.308 of road length of Section-I, II, III & IV has been taken over out of 378 km. The contractor has been instructed to complete all the pending works within a shortest period of time.

- Also 57.4Km of road stretches are substantially completed by the contractor.

Culverts (AS PER NEW RECONFIGURATION)

Bridges

Encumbrance

ROBs

Expenditure incurred as on 31ST December 2009

Value of L.D. Imposed

Total amount of LD till November 2009 for section-I, II, III & IV works out to: Rs 681,005,503

Maximum Amount of LD as per letter No. 4361/2004/TNRSP/P-2 dated 16.12.2009 = Rs. 550,700,000

Amount of L D already recovered till courts Injuncture i.e. upto 31st January Rs.  90,048,802.00

Balance withheld amount of LD as on 30th November 2009.                          Rs. 460,651,198