#### 2. Civil Construction Works for Contract Package TNRSP 02

| 1 | Contract Package | : | TNRSP 02 |
| --- | --- | --- | --- |
| 2 | Name of work | : | Upgradation of Road from Nagapatinam to Katumavadi |
| 3 | Name of Contractor | : | IRCON International Ltd-SUMBAR MITHRA JAYA (JV) |
| 4 | Name of Consultant | : | Sheladia Associates Inc., |
| 5 | Original Contract value | : | Rs.198,77,31,104/- |
| 6(a) | Variation Approved /Proposed | : | Rs. 328016740.34/- (16.511%) excluding 6 ROBs in P 01 |
| 6(b) | Variation issued for 6 ROBs (Under contract package 01) | : | Rs. 23, 11,12,434/- |
| 7 | Total length of Project Road | : | 118.60 km |
| 8 | Physical progress | : | Achieved 87.75% Target 97.80% |
| 9 | Financial progress | : | Achieved 85.22% Target 97.80% |
| 10 | Expenditure incurred | : | 109.28% (includes price escalation ) |
| 11 | (a) Original contract value + Variations | : | 2315747844/- |
|  | (b) Revised contract price | : | 21750 lakhs |
| 12 | Upto date value of work done | : | 19077lakhs |
| 13 | Remaining work | : | 2673 lakhs (app) |

Status

| Section | Length (in Km) | Date of Start | Scheduled date of Completion | EOT granted if any | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 17.60 | 10-02-2005 | 09-08-2006 | 31-07-2007 | Taking Over Certificate for section 1 (excluding bridge no. 58) issued on 10 October 2007 ( Ch. 391+400 to 408+971)(17.57 km). Bridge no. 58 completed on 28 March 2008. DLC issued for Section 1 on 10.03.2009. |
| 2 | 30.40 | 10-08-2005 | 09-04-2007 | 22-01-2008 - Cleared Stretches | Taking over certificate in Section 2 (14.735 km) issued on 17 March 2008. 7.2 km on 16 May 2008. (373+000 to 391+100(18.1 Km)& MPT Bypass 1+000 to 4+835 (3.835 Km). Taking over certificate for the remaining length (excluding ROB) has been issued on 15 March 2009. As per Contractor’s revised Programme. completion of ROB 31 March 2010 |
|  |  |  |  | 15-03-2009 – Encumbered Stretches of 2.96km length and on 28/04/09 for Box culvert (replacing bridge no. 49) with approach |  |
|  |  |  |  | 31-12-2009 for ROB |  |
| 3 | 22.70 | 10-12-2005 | 09-06-2007 | 22-01-2008 - Cleared Stretches | Taking over certificate in section 3 (7.468 km) issued on 17 March 2008. 8.3 km on 28 July 2008. (343+672 to 346+800, 349+320 to 353+660, 353+800 to 357+800 & 358+200 to 362+500 ( 15.768 km). Taking over certificate for remaining length (excluding ROB and Br 47 with approaches ) has been issued on 31 March 2009 As per Contractor’s revised Programme. Completion of ROB 31 March 2010 |
|  |  |  |  | 31-03-2009 – Encumbered Stretches of 5.018 km and 30-11-09 for bridge no. 47 with approaches |  |
|  |  |  |  | 31-12-2009 for ROB |  |
| 4 | 47.90 | 10-05-2006 | 09-02-2008 | 30-09-2009 for road works in section 4 & NGP Bypass (excluding Vettar bridge , B39 and ROB) | Taking over certificate for part length(on substantial completion) issued from km301+040 to 317+050 (16.01 km) on 1 April 2009. Taking over certificate from km 317+050 to 324+500 (7.45 km)& from Km 331+200 to 335+600 (4.40 km ) on 24/06/09. Taken over certificate issued from km 324+500 to 331+200 (6.70 km) and from km 335+600 to 338+433 (2.833 km) on 30 September 2009. As per Contractor’s revised Programme. Completion of ROB 31 March 2010, Section 4; 31 Mar. 2010;Vettar Bridge 30 Sep. 2010 and Bridge. no 31&32 Oct. 2010. |
|  |  |  |  | 31-10-2009 for Vettar bridge+ |  |
|  |  |  |  | 15-05-2009 for Bridge no. 39 |  |
|  |  |  |  | 31-12-2009 for ROB Box Culvert at Ch. 6+690 t 0+407 (31/10/09) Box Culvert at 8+540 (30/11/09) |  |

Bridges

Bridges

ROBs

Encumbrance (in Km)

Nil

Expenditure incurred (in lakhs)

Pending issues with the Employer

| SL.No | Subject | Reference | Remarks |
| --- | --- | --- | --- |
| 1 | Variation no. 31 –Construction of Speed Breakers Using Reflective Studs | 02/cks/5.5.1.28/001 Dt.03.03.2009 | Approval awaited from TNRSP |
| 2 | Variation no. 32 – Construction of a skew Box culvert (3v of 2x3m) replacing Bridge no. 49 Ch. 368+963 in Section 2 | 02/cks/5.5.1.18/009 Dt. 14.03.09 |  |
| 3 | Variation no. 33 Reconstruction of bridge no. 31 & 32 in section 04 (Revised) | 02/cks/5.5.1.29/006 Dt. 10.09.09 |  |
| 4 | Variation no. 34 - General items (Bill 1(a) | 02/cks/5.5.1.19/003 Dt. 04.04.09 |  |
| 5 | Variation no. 35 – Special repair to existing bridge no. 31 | 02/cks/5.5.1.29/002 Dt. 09.07.09 |  |
| 6 | Variation no. 36 – Soil exploration for bridge no. 31 and permanent office building | 02/cks/5.5.1.29/002 Dt. 09.07.09 |  |
| 7 | Variation no. 37 – Construction supporting structure for TWAD pipeline at Bridge (site ) no. 47 (revised) | 02/cks/5.5.1.29/005 Dt. 31.08.09 |  |
| 8 | Variation no. 38 - Dynamic pile load test | 02/cks/5.5.1.29/005 Dt 15.10.09 |  |
| 9 | Variation no. 39 – Providing office accommodation for Engineer and Engineer’s representative | 02/cks/5.5.1.30/001 Dt. 04.10.09 |  |