#### 5. Civil Construction Works for Contract Package TNRSP 05

| Date of Agreement | 23.06.2008. |
| --- | --- |
| Period of Contract | 18 Months + Defect liability period of 365 days. |
| Schedule Date of Start | 21.07.2008. |
| Schedule Date of Completion | 20.01.2010. |
| Likely Date of Completion | July 2010. |
| Original Contract value | Rs. 35,29,83,655/- |
| Total Length of Road | 10.4 km |
| Value of Variation for service ducts at road junction | Rs.14,08,118/- |

Physical Progress :

Progress achieved during this quarter is 2.44% against 15.13% targeted. Total progress up to the end of December is 39.77% against 96.00% scheduled. The contract is therefore behind schedule by 56.23%.

The Revised Updated Programme up to December is 46.25% of Contract value and the achievement is 39.77%. Approval of updated programme is being given after receipt of required clarifications from Contractor.

Contract Sections

| Section 1.Milestone | Physical Progress | Date of Completion | Remarks |
| --- | --- | --- | --- |
| Milestone 1 Total length 5.69km | Handed over on 21.07.2008 Clearing and grubbing completed, Earth work - 5 Km GSB – 3.76 Km WMM- 3.36 km ROB retaining wall in progress. | 20.01.2010 | All the 5 slab culverts has been completed except parapet wall and pitching Out of two 1 is completed and another may stand deleted. Out of 2 minor bridges, 1 is in progress and another is yet to be started. |
| Milestone 2 Total length 4.710km | Land had handed over land on different dates as under: Ch 4+000 to Ch 4+710 - 31.07.2009 Ch 0+000 to Ch 2+080 - 31.08.2009 Ch 3+140 to Ch 4+000 - 28.10.2009 Ch 2+080 to Ch 3+140 - 30.10.2009. | 9 months from the date of handing over. | Earth work is in progress. |