TAMILNADU ROAD SECTOR PROJECT

IBRD Loan Account No. 4706-IN

Quarterly Progress Report for the Quarter ending 31.12.2009

| Description of Consultancy | : | Consultancy Services for Technical Assistance to Establish a Road Management System (RMS) on the Core State Road Network. |
| --- | --- | --- |
| Name of Consultant | : | M/s. Mouchel Parkman Services Limited, London and M/s. Span Consultant Pvt. Ltd, India (J.V). |
| Original contract amount | : | INR =19,904,157+ USD= 221,900 + GBP= 514,457 including all taxes (equivalent - Rs 6.89Cr.) |
| Contract Amount after Variation Order No.1. | : | INR 20724385 + USD 227574 + GBP 531203 |
|  |  | Initial implementation 18 Months; Operational support 22 months – (Commencement of service 08.03.2005). |

|  | Initial Implementation | Operational Support |
| --- | --- | --- |
| Original completion | 07.09.06 | 07.07.2008 |
| Extended completion | 30.09.08 | 30.07.2010 |

| Sl. No. | Physical activity | Physical progress | Financial progress | Expenditure Rs. In Lakhs |
| --- | --- | --- | --- | --- |
|  |  | Planned in % | Achieved in % | Planned in % | Achieved in % |  |
| 1. | First Payment on submission of Bank guarantee. | 20% (Physical Progress does not arise) | 20% payment (Physical Progress does not arise) | 20% | 20% | 146.75 |
| 2. | Inception Report | Inception Report | Inception report Approved | 10% | 10% | 73.38 |
| 3. | First quarter – final report on needs analysis and overall system architecture and progress on data collection. | Deliverable to be Submitted | Submitted and approved by review committee subject to agreements on decisions of review committee on key contractual issues. Acceptance of consultants received and payment made. | 4.5% | 4.5% | 33.73 |
| 4. | Second quarter – Draft final report on training needs assessment and progress on data collection. | Deliverable to be Submitted | Revised report along with Compliance statement and progresses on data collection approved by Review committee payment made. | 4.5 | 4.5 | 31.74 |
| 5. | Third quarter Traffic Information System, Pavement Management System, Progress on Data Collection | Deliverable to be submitted | Draft Report on TIS & PMS compliance testing and progress on data collection received and payment made | 4.5 | 4.5 | 31.06 |
| 6. | Fifth quarter – Draft report on Annual Road conditions and progress on data collection. | Deliverable to be Submitted | Draft Report on Annual Road conditions received and payment made. | 4.5 | 4.5 | 32.20 |
| 7. | Sixth quarter – Draft Report on Annual Road condition | Deliverable to be Submitted | Report submitted. Approved by Review Committee and payment made | 4.5 | 4.5 | 32.20 |
| 8. | Seventh quarter – Draft Final Report on RMS User Manual | Deliverable to be Submitted | Report submitted. Approved by Review Committee and payment made | 4.5 | 4.5 | 32.20 |
| 9. | Eighth quarter – Final Report on Road Data Collection Manual | Deliverable to be Submitted | Report submitted. Approved by Review Committee and payment made | 4.5 | 4.5 | 32.20 |
| 10. | Fourth quarter deliverables – Draft Final Report on TMS &TIS compliance testing | Deliverable to be Submitted | Report submitted. And approved by Review Committee and payment made. | 4.5 | 4.5 | 32.20 |
| 11. | Ninth quarter deliverables. | Deliverable to be Submitted | Ninth quarter deliverable submitted. Review Committee to comment on the report. | 4.5% | 0.0 | 0.0 |
| 12. | Tenth to Twelfth quarter deliverable. | Deliverable to be Submitted | - | 4.5% for each | 0.0 | 0.0 |
| 13. | Additional ROMDAS survey – Variation Order No. 1. | completed | 100% payment completed. AMC for ROMDAS is being carried and to extended by consultant till 2011. | 100 | 100 | 23.74 |

- ROMDAS survey completed for 100 percent of length.

- All the surveys like traffic census, axle load, BBD and CBR tests and subgrade strength tests completed.

- ROMDAS survey completed for additional scope of work (4000 km).

- Software development & testing completed.

- Training for engineers completed